## Slide 1
Robotic Process Automation in Official Statistics
project proposal
Zoltán Vereczkei
Methodology Department
Hungarian Central Statistical Office
zoltan.vereczkei@ksh.hu
2022 Workshop on the Modernisation of Official Statistics
22nd November, 2022

## Slide 2: RPA in a nutshell
Source: YouTube: https://www.youtube.com/watch?v=g-s-XXM2T_I .

## Slide 3: Official statistics is ready for RPA
Pressure to speed things up
Need for fast ROI from innovation/modernisation
Complex architectures: many IT systems, tools, services
Pressure to increase transparency
Automate processes
Maintain/improve quality
Modernise
Free up resources
Internal transparency
External transparency
Compatibility with our existing infrastructure
Challenges we face
The volume of manual work
What we really need
Save money
Compliance with HLG vision

## Slide 4: What can we do together?
EXPLORE
The technology and the potential together
LEARN
Plan, conduct, assess pilots and learn together
DEFINE
The business case, expectations, „the road” together
CONCLUDE
Guidance for the community, results to take back home
Template original source: Slidesgo and Freepik.
PROJECT LAUNCH
WP1: Review of current RPA practices and tools
PHASE 1
WP2: Business case / identifying processes with good RPA potential
WP3: Define and undertake common pilots using RPA
PHASE 2
WP4: Assessment of RPA solutions
WP5: Recommendations for using RPA solutions in official statistics
WP6: Visibility and communication
PROJECT CLOSING
WP7: Project management, reporting

## Slide 5: Project timeline (1 year)
January 2023
Project launch
March 2023
Start of Phase 1
July 2023
End of Phase 1
Start of Phase 2
December 2023
End of Phase 2
Project closing
Common understanding, project planning
Project launch
Review
Identify good candidate processes
Common first pilots
Phase 1
Assessment of results
Producing recommendations
Communication material
Phase 2
Reporting
Final assessment
Project closing
Template original source : Slidesgo and Freepik.
December 2023
December 2024
or 2 years…

## Slide 6: Project results
Knowledge and pilots done together to better understand the use of RPA
Common guidance for the official statistical community on how to use RPA
Practical working solution for automation
Ideas on common processes present in NSOs: recommendations where to implement RPA in our NSOs
Communication tools on how to explain this to our different stakeholders
Countries / organisations already committed to this project proposal:
Statistics Canada
Hungarian Central Statistical Office

## Slide 7
Thank you!
Comments, questions, suggestions?
Zoltán Vereczkei
Methodology Department
Hungarian Central Statistical Office
zoltan.vereczkei@ksh.hu